## Hoja1
Target : Project Proposal Week 1-Day 3 - ALPHA INSGHTS
Team | Damian Buch | Martin Menedez | Mauro Cadme | Miguel Salas | Gisela Medina
Done
| Set actual situation, goals, reaching, KPIs, technological stack, work methodology, team roles, deliverables. | Set actual situation, goals, reaching, KPIs, technological stack, work methodology, team roles, deliverables. | Set actual situation, goals, reaching, KPIs, technological stack, work methodology, team roles, deliverables. | Set actual situation, goals, reaching, KPIs, technological stack, work methodology, team roles, deliverables. | Set actual situation, goals, reaching, KPIs, technological stack, work methodology, team roles, deliverables.
| Set company's name | Set company's name | Set company's name | Set company's name | Set company's name
|  |  | EDA |  | Deliverable
Issues
| Found an Olist API made to share information with their clients; not really usefull for the project | Found an Olist API made to share information with their clients; not really usefull for the project | Found an Olist API made to share information with their clients; not really usefull for the project | Found an Olist API made to share information with their clients; not really usefull for the project | Found an Olist API made to share information with their clients; not really usefull for the project
Pending AWS free trial
Doing- To do's
| Refine final documentation | Refine final documentation | Refine final documentation | Refine final documentation | Refine final documentation
| Powerpoint presentation | Speech preparation | EDA documentation | Speech preparation | Powerpoint presentation
| ETL | ETL | ETL | ETL | ETL
|  | Gantt diagram |  |  | Next weeks Trello
Project Risk |  |  | Percent complete
Lack of Backup | Replicar el DW on premise
Lack of Cloud tools knowledge |  |  | Week 1