## Hoja1
Target : Complete ETL Workflow and DB Creation
Team | Damian Buch | Martin Menendez | Mauro Cadme | Miguel Salas | Gisela Medina
Done
| Creation of Datawarehouse | Final Project README in GitHub Repository | First ETL | Documents Week 1 | Prepare week's tasks
Issues
AWS not respoding yet
Doing- To do's
| Getting knowledge about AWS tools - Incremental loading - Pipelines | Getting knowledge about AWS tools | Data Revision and Normalization | Data Revision and Normalization | Data Revision and Normalization
|  | Week 2 Dailies Report | Entity Relationships | Entity Relationships | Entity Relationships
Project Risk |  |  | Percent complete
|  |  | Week 2 | 10%