## Hoja1
Target : Complete ETL Workflow and DB Creation
Team | Damian Buch | Martin Menendez | Mauro Cadme | Miguel Salas | Gisela Medina
Done
| Create workflow detailing technologies | Getting knowledge about AWS tools | Data Revision and Normalization in Python | Data Revision and Normalization in Python | Data Revision and Normalization in Python
| Import datasets to AWS | Domain Acquisition and Primary Web Creation |  |  | Found World bank data for expansion analysis
Issues
AWS not respoding yet
Doing- To do's
| Week 2 Dailies Report | Data Revision and Normalization in AWS (Glue DataBrew Service) | Analyze World Bank data | Data Revision and Normalization in AWS (Glue DataBrew Service) | Analyze World Bank data
|  |  | Entity Relationships | Entity Relationships | Entity Relationships
Project Risk |  |  | Percent complete
|  |  | Week 2 | 10%