## Hoja1
Target : Complete ETL Workflow and DB Creation
Team | Damian Buch | Martin Menendez | Mauro Cadme | Miguel Salas | Gisela Medina
Done
| incremental automation code | Data Revision and Normalization in AWS (Glue DataBrew Service) | Analyze World Bank data | Data Revision and Normalization in AWS (Glue DataBrew Service) | Analyze World Bank data
|  | Domain Acquisition and Primary Web Creation |  |  | Prepare Data dictionary
Issues
AWS not respoding yet
Doing- To do's
| incremental automation code- in progress | create RDS and prepare validation Data | Prepare validation Data | Create RDS | Prepare Entity relation
Prepare documentation
Project Risk |  |  | Percent complete
|  |  | Week 2 | 20%